## Projects
project_name | type | value | mandatory | dependencies | optimistic_weeks | likely_weeks | pessimistic_weeks | earliest_start_month | probability | ds_month_1 | ds_month_2 | ds_month_3 | ds_month_4 | ds_month_5 | ds_month_6 | geo_month_1 | geo_month_2 | geo_month_3 | geo_month_4 | geo_month_5 | geo_month_6 | pm_month_1 | pm_month_2 | pm_month_3 | pm_month_4 | pm_month_5 | pm_month_6
Seismic Reprocessing Platform | large | 95 | yes |  | 16 | 22 | 32 | 0 | 1 | 3 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 3 | 2 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Well-Log ML Predictor | medium | 80 | yes |  | 10 | 14 | 20 | 0 | 1 | 2 | 3 | 3 | 2 |  |  | 1 | 1 | 1 | 0 |  |  | 1 | 1 | 1 | 1
Reservoir Simulation Dashboard | large | 90 | yes | Seismic Reprocessing Platform | 14 | 20 | 28 | 5 | 1 | 2 | 3 | 4 | 3 | 2 |  | 2 | 2 | 2 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1
Automated Core Analysis | medium | 75 | no |  | 8 | 12 | 18 | 2 | 0.85 | 2 | 2 | 2 |  |  |  | 2 | 3 | 2 |  |  |  | 1 | 1 | 0
Production Forecasting Upgrade | small | 65 | yes |  | 5 | 8 | 12 | 1 | 1 | 2 | 2 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1
Geospatial Data Lake | large | 85 | no |  | 18 | 26 | 36 | 0 | 0.7 | 3 | 4 | 4 | 3 | 3 | 2 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Environmental Compliance Tracker | small | 70 | yes | Well-Log ML Predictor | 4 | 6 | 10 | 4 | 1 | 1 | 2 |  |  |  |  | 1 | 1 |  |  |  |  | 1 | 1

## Tasks
project_name | task_id | task_name | optimistic_weeks | likely_weeks | pessimistic_weeks | predecessors | data_scientists | geoscientists | project_managers
Seismic Reprocessing Platform | S1 | Requirements & Scoping | 2 | 3 | 5 |  | 1 | 2 | 0
Seismic Reprocessing Platform | S2 | Data Ingestion Pipeline | 3 | 5 | 8 | S1 | 3 | 0 | 0
Seismic Reprocessing Platform | S3 | Processing Algorithm Dev | 4 | 6 | 10 | S1 | 2 | 2 | 0
Seismic Reprocessing Platform | S4 | Integration & Testing | 3 | 4 | 6 | S2, S3 | 2 | 1 | 0
Seismic Reprocessing Platform | S5 | Deployment & Handover | 2 | 3 | 5 | S4 | 1 | 0 | 1
Well-Log ML Predictor | W1 | Data Audit & Cleaning | 2 | 3 | 5 |  | 1 | 1 | 0
Well-Log ML Predictor | W2 | Feature Engineering | 2 | 3 | 5 | W1 | 2 | 0 | 0
Well-Log ML Predictor | W3 | Model Training & Tuning | 3 | 4 | 6 | W2 | 2 | 0 | 0
Well-Log ML Predictor | W4 | Validation & Reporting | 2 | 3 | 4 | W3 | 1 | 1 | 1
Reservoir Simulation Dashboard | R1 | Dashboard Architecture | 2 | 3 | 4 |  | 2 | 0 | 1
Reservoir Simulation Dashboard | R2 | Simulation Engine Wrapper | 4 | 6 | 9 | R1 | 3 | 2 | 0
Reservoir Simulation Dashboard | R3 | Visualization Layer | 3 | 4 | 6 | R1 | 2 | 0 | 0
Reservoir Simulation Dashboard | R4 | User Testing & Polish | 3 | 5 | 8 | R2, R3 | 1 | 1 | 1
Automated Core Analysis | C1 | Image Pipeline Setup | 2 | 3 | 5 |  | 1 | 1 | 0
Automated Core Analysis | C2 | Classification Model | 3 | 4 | 6 | C1 | 2 | 1 | 0
Automated Core Analysis | C3 | Integration & QA | 2 | 3 | 5 | C2 | 1 | 2 | 0
Production Forecasting Upgrade | P1 | Current Model Audit | 1 | 2 | 3 |  | 1 | 1 | 0
Production Forecasting Upgrade | P2 | Algorithm Improvements | 2 | 3 | 5 | P1 | 2 | 0 | 0
Production Forecasting Upgrade | P3 | Back-testing & Deploy | 1 | 2 | 3 | P2 | 1 | 0 | 1
Geospatial Data Lake | G1 | Cloud Architecture Design | 3 | 4 | 7 |  | 2 | 0 | 1
Geospatial Data Lake | G2 | Data Migration | 4 | 7 | 10 | G1 | 3 | 1 | 0
Geospatial Data Lake | G3 | API & Access Layer | 3 | 5 | 8 | G1 | 2 | 0 | 0
Geospatial Data Lake | G4 | Spatial Indexing Engine | 3 | 5 | 7 | G2 | 2 | 2 | 0
Geospatial Data Lake | G5 | Testing & Documentation | 2 | 3 | 5 | G3, G4 | 1 | 1 | 1
Environmental Compliance Tracker | E1 | Regulatory Data Mapping | 1 | 2 | 3 |  | 1 | 1 | 0
Environmental Compliance Tracker | E2 | Alert & Reporting Module | 2 | 3 | 5 | E1 | 2 | 0 | 1
Environmental Compliance Tracker | E3 | Stakeholder Review | 1 | 1 | 2 | E2 | 0 | 0 | 1

## Config
TEAM CAPACITY
Role | Headcount
data_scientists | 8
geoscientists | 5
project_managers | 4
PLANNING
horizon_months | 12
HISTORICAL DURATIONS (weeks)
Category | Durations (comma-separated)
small | 6, 8, 7, 9, 7, 8, 10, 6
medium | 12, 15, 14, 16, 13, 15
large | 20, 24, 22, 26, 23, 28, 21